## Sheet1
ID | Task Name | Duration |  | 9 feb '15 (wk 1) | [6 empty] | 16 feb '15 (wk2) | [6 empty] | 23 feb'15 (vacation) | [6 empty] | 2 march '15 (wk3) | [6 empty] | 9 march '15 (wk4) | [6 empty] | 16 march '15 (wk5) | [6 empty] | 23 march '15 (wk6) | [6 empty] | 30 march '15 (wk7) | [6 empty] | 6 apr '15 (wk8) | [6 empty] | 13 apr '15 (wk9) | [6 empty] | 20 apr '15 (wk10) | [6 empty] | 27 apr '15 (wk11) | [6 empty] | 4 mei '15 (wk12) | [6 empty] | 11 mei '15 (wk13) | [6 empty] | 18 mei '15 (wk14) | [6 empty] | 25 mei '15 (wk15) | [6 empty] | 1 juni '15 (wk16) | [6 empty] | 8 juni '15 (wk17) | [6 empty] | 15 juni '15 (wk18) | [6 empty] | 22 juni '15 (wk19) | [6 empty] | 29 juni '15 (wk20)
|  |  | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
1 | Kick-off project | 1 day | bar: 9 feb '15 (wk 1) M to 9 feb '15 (wk 1) T
2 | Cooperation agreement | 7 days | bar: 9 feb '15 (wk 1) T to 16 feb '15 (wk2) M
3 | Action plan | 8 days | bar: 16 feb '15 (wk2) M to 23 feb'15 (vacation) M
4.1 | research paper 1 | 40 days | bar: 23 feb'15 (vacation) M to 30 march '15 (wk7) F
4.2 | research paper 2 | 40 days | bar: 23 feb'15 (vacation) M to 30 march '15 (wk7) F
5.1 | Calculations | 8 days | bar: 9 march '15 (wk4) M to 16 march '15 (wk5) M
5.2 | Simulations | 10 days | bar: 16 march '15 (wk5) M to 23 march '15 (wk6) W
5.3 | Calculation report | 10 days | bar: 23 march '15 (wk6) W to 30 march '15 (wk7) S
6.1 | Assessment (PRO-Q2-pj1) | 1 day | bar: 13 apr '15 (wk9) M to 13 apr '15 (wk9) S
6.1 | Design PCB layout (preamp.) | … days
6.2 | Built preamp. | … days
6.3 | Test preamp. | … days
7.1 | Design PCB layout (power amp.) | … days
7.2 | Build power amplifier | … days
7.3 | Test power amplifier | … days
8.1 | Design PCB layout (power sup.) | … days
8.2 | Build power supply | … days
8.3 | Test power supply | … days
9.1 | Design DCU | … days
9.2 | Build DCU | … days
9.3 | Test DCU | … days
10.1 | Assemble speaker system | … days
10.2 | Test speaker system | … days
11.1 | Measurements | … days
11.2 | Measurement report | … days
12 | Draft of the final design report | … days
13 | Draft of the poster presentation | … days
14 | Final design report | … days
15 | demostration of the complete system | … days
16 | Poster presentation | … days
Task-color assign to the members:
All members =
Kevin Oei =
Andrew Lau =
Daan Conijn =
Koen van Vliet =
Otherwise stated (read comments) =
unkwown (will be known in the future)=
Note on F3: Milestone 1: Attend the kick-off
Note on L4: Author: Kevin Oei worked on the cooperation agreement and all the project members discussed and signed the cooperation agreement.
Note on S5: Author: The Action Plan consist of 10 chapters. The chapters are assigned to the following members: Daan Conijn wrote chapter 5 and 8. Andrew Lau wrote chapter 1, 6 and 9 Kevin Oei wrote chapter 2, 3 and 7 Koen van Vliet wrote chapter 4 and 10
Note on BF6: Author: Koen van Vliet and Andrew Lau will research on subject 5 (difference between bridge and unbridge amplifiers)
Note on BF7: Author: Daan Conijn and Kevin Oei will research on subject 3 (difference between bridge and unbridge amplifiersEffect of EMI and noise on audio amplifiers)
Note on AN8: It is unkwown who will carry out this task
Note on AW9: It is unkwown who will carry out this task
Note on BG10: Milestone 2: Delivering the two researchpapers and calculation report
Note on BT11: Author: It is still unkown when the first assessment will take place but it's somewhere in this week.
Note on BU11: Milestone 3: Attending and complete the first assessment. Failure is not an option.